## AppName-MonthlyUsers-MonthlyCos
Quarter | Phase | Action | Apps | Cost Before | Cost After | Savings | Status | Platform Blocker
Q1 2026 | KILL | Retire + Redirect | Batch Jobs, Admin Portal | $20k/mo | 0 | $240k/yr | 🟢 DONE | None
Q1 2026 | LIFT | Auth Service → K8s | Auth Service | $8k/mo | $6k/mo | $24k/yr | 🟢 DONE | Ch21 Helm
Q2 2026 | MODERNIZE | User Portal → Next.js | User Portal | $18k/mo | $8k/mo | $120k/yr | 🔄 Ch18 | Self-service portal
Q2 2026 | STRANGLER | Legacy CRM → Microservices | Legacy CRM | $45k/mo | $20k/mo | $300k/yr | 🔄 Ch18 | API Gateway
Q3 2026 | REPLATFORM | Payment API → Bun | Payment API | $12k/mo | $5k/mo | $84k/yr | ⏳ Ch19 | Event schemas
Q3 2026 | KILL | Inventory → Retire | Inventory | $62k/mo | 0 | $744k/yr | ⏳ Ch25 | None
Q4 2026 | EXTRACT | Order Service | Order Service | $35k/mo | $15k/mo | $240k/yr | ⏳ Ch18 | Outbox pattern